## Overview
			Retrospective 1			Retrospective 2				Retrospective 3			Retrospective 4

Kickoff	Sprint 1	Sprint 2	Sprint 3	Sprint 4	Sprint 5	Sprint 6	Sprint 7	Sprint 8	Sprint 9	Sprint 10	Sprint 11	Sprint 12	Sprint 13	Sprint 14	Sprint 15	Sprint 16	Sprint 16
	W08	W09	W10	W11	W12	W13	W14	W15	W16	W17	W18	W19	W20	W21	W22	W23	W23

	project plan / completed				basic architecture / fixed		final technology fixed			alpha release			beta release			feature / freeze	code / freeze	documentation / completed
				basic requirements & / analysis completed			testing concept fixed											presentation / prepared
			task description / fixed															final release / / submission
		license & / usage rights defined

## Sprint Details
Sprint	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Tag	0.1.0	0.2.0	0.3.0	0.4.0
Date	20.02.2018 – 27.02.2018	27.02.2018 - 06.03.2018	06.03.2018 – 13.03.2018	13.03.2018 – 20.03.2018
Milestones	- license & usage rights defined	- task description fixed	- basic requirements & analysis completed	- basic architecture fixed
Time Budget	40	40	40	40
Tasks	- setup remaining project infrastructure / - read ietf draft, XEP standards etc. / - compile list of open questions / - begin with chapter “initial situation” / - analyze existing python proof-of-concept	- collect non-functional requirements (NFRs) / - compile set of user stories / - draw wireframes / - research frameworks and technology: Prepare architectural decisions	- extend NFRs, user stories, wireframes / - make first architectural decisions / - further framework and technology research / - implement proof of concepts for ciritical components	- make big architectural decisions / - implement proof of concepts for ciritical components
Documents / / Chapters / / Artefacts		- chapter "Initial Situation" completed / - signed task description

Sprint	Sprint 5	Sprint 6	Sprint 7	Sprint 8
Tag	0.5.0	0.6.0	0.7.0	0.8.0
Date	20.03.2018 – 27.03.2018	27.03.2018 – 03.04.2018	03.04.2018 – 10.04.2018	10.04.2018 – 17.04.2018
Milestones		- final technology fixed / - testing concept fixed
Time Budget	40	40	40	40
Tasks	- implement proof of concepts for ciritical components / - draft testing concept	- implement proof of concepts for ciritical components / - finalise testing concept	- Implement most important user stories / - make further architectural decisions	- Implement most important user stories / - make further architectural decisions
Documents / / Artefacts		- Chapter "Our Approach" completed

Sprint	Sprint 9	Sprint 10	Sprint 11	Sprint 12
Tag	0.9.0	0.10.0	0.11.0	0.12.0
Date	17.04.2018 – 24.04.2018	24.04.2018 – 01.05.2018	01.05.2018 – 08.05.2018	08.05.2018 – 15.05.2018
Milestones	- alpha release			- beta release
Time Budget	40	40	40	40
Tasks	- Implement most important user stories / - make further architectural decisions / - write integration tests	- Implement secondary user stories / - write integration tests	- Implement secondary user stories / - write integration tests	- Implement secondary user stories / - write integration tests
Documents / / Artefacts	- alpha release bundle			- beta release bundle

Sprint	Sprint 13	Sprint 14	Sprint 15	Sprint 16
Tag	0.13.0	0.14.0	0.15.0	0.16.0
Date	15.05.2018 – 22.05.2018	22.05.2018 – 29.05.2018	29.05.2018 – 05.06.2018	05.06.2018 – 12.06.2018
Milestones			- future freeze	- code freeze
Time Budget	40	40	40	80
Tasks	- Implement remainging user stories / - Improve code base / - write integration tests	- Implement remainging user stories / - Improve code base / - write integration tests	- Implement remainging user stories / - Improve code base / - write integration tests	- fix eventual bugs / - write documentation
Documents / / Artefacts				- final release bundle / - poster / - abstract

Sprint	Sprint 17
Tag	1.0.0
Date	12.06.2018 – 15.06.2018
Milestones	- documentation completed / - presentation prepared / - final release / submission
Time Budget	40
Tasks	- write documentation / - submit documents
Documents / / Artefacts	- personal reports / - management summary / - presentations / - time accounting