## Report
Time Accounting

Time Spent per Sprint
hours spent

We spent on average 42.39 hours per sprint conforms to the intended 40 hours. The work, however, is not distributed equally over the sprints.

Time Spent per Component

As intended, we spent the most time on the application. The management that includes project and sprint planning, standup and advisory meetings, as well as infrastructure tasks, took approximately a quarter of the projects time budget. We also spent a lot of time on the final submission document, as it is an essential part of the bachelor thesis.

Estimated Cost

Using the hourly wage from the module Software Engineering 2, the total project costs would be 58689 CHF in practice.

Time Spent per Person

## pivot_sprints
Esprint	Sum - Hours
Sprint 0	11.5
Sprint 1	34.5	40
Sprint 2	39.75	40		Average:	42.3875
Sprint 3	39.25	40
Sprint 4	44.75	40
Sprint 5	38.5	40
Sprint 6	25.5	40
Sprint 7	66.45	40
Sprint 8	70	40
Sprint 9	24.5	40
Sprint 10	67.25	40
Sprint 11	16.75	40
Sprint 12	43.75	40
Sprint 13	48.25	40
Sprint 14	76.75	70
Sprint 15	30.75	60
#N/A	2.25	30
Total Result	680.45

## pivot_components
Component	Sum - Hours		Kosten		Kosten pro Personentag	CHF 690.00
Application	408.25	60.00%	CHF 35'211.56		Kosten pro Arbeitsstunde	CHF 86.25
Final Submission Document	148.5	21.82%	CHF 12'808.13		Quelle: SE2 aufwandschaetzung.pdf, F45, Dr. Daniel Keller
Management	108.2	15.90%	CHF 9'332.25
Poster	6.5	0.96%	CHF 560.63
Presentation	2.5	0.37%	CHF 215.63
Project Plan	6.5	0.96%	CHF 560.63
(empty)
Total Result	680.45		CHF 58'688.81

## pivot_users
Full name	Sum - Hours
Fabian Hauser	339.95
Raphael Zimmermann	340.5
(empty)
Total Result	680.45

## worklogs
Issue Key	Issue summary	Hours	Work date	Username	Full name	Period	Account Key	Account Name	Account Lead	Account Category	Account Customer	Activity Name	Component	All Components	Version Name	Issue Type	Issue Status	Project Key	Project Name	Epic	Epic Link	Work Description	Parent Key	Reporter	External Hours	Billed Hours	Issue Original Estimate	Issue Remaining Estimate	Sprint	Esprint
XGB-50	Abstract in DAB-Tool	0.75	2018-6-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-50		fhauser	0	0.75	1	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-218	Make page size configurable	0.5	2018-6-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-218		rzimmerm	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-49	Create Poster	0.5	2018-6-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Poster	Poster	Poster		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-49		fhauser	0	0.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-197	Enhance Code Documentation and Structure	1.5	2018-6-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-197		fhauser	0	1.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-216	Investigate BOSH timeout handling and (if possible) allow to configure it	0.5	2018-6-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-216		rzimmerm	0	0.5	3	1	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-49	Create Poster	6	2018-6-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Poster	Poster	Poster		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-49		fhauser	0	6	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-197	Enhance Code Documentation and Structure	1	2018-6-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-197		fhauser	0	1	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-197	Enhance Code Documentation and Structure	4	2018-6-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-197		fhauser	0	4	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-216	Investigate BOSH timeout handling and (if possible) allow to configure it	0.5	2018-6-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-216		rzimmerm	0	0.5	3	1	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-216	Investigate BOSH timeout handling and (if possible) allow to configure it	1	2018-6-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Review	XGB	XMPP-Grid Broker			Working on issue XGB-216		rzimmerm	0	1	3	1	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-218	Make page size configurable	1.5	2018-6-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-218		rzimmerm	0	1.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-215	Complete Glossary	2.25	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-215		fhauser	0	2.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-57	Write personal report rzimmerm	1.25	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-57		fhauser	0	1.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-58	Write personal report fhauser	0.25	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-58		fhauser	0	0.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-57	Write personal report rzimmerm	0.5	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-57		fhauser	0	0.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-215	Complete Glossary	2.75	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-215		fhauser	0	2.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-58	Write personal report fhauser	0.25	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-58		fhauser	0	0.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-212	Discuss Speed, Scalability and Concurrency in the architecture	0.25	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-212		rzimmerm	0	0.25	2	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-58	Write personal report fhauser	0.25	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-58		fhauser	0	0.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-212	Discuss Speed, Scalability and Concurrency in the architecture	0.5	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-212		rzimmerm	0	0.5	2	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-219	Update Project Plan	1	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-219		fhauser	0	1	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-219	Update Project Plan	0.5	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-219		fhauser	0	0.5	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-58	Write personal report fhauser	0.5	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-58		fhauser	0	0.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-222	Sprint Planning Sprint 15	1	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-222		fhauser	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-222	Sprint Planning Sprint 15	1	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-222		fhauser	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-58	Write personal report fhauser	0.75	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-58		fhauser	0	0.75	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
XGB-207	Write section achieved result	2.5	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-207		rzimmerm	0	2.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-163	Abstract and Mgmt Summary Review	0.5	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-163		rzimmerm	0	0.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
XGB-209	Write section lessons learned	0.25	2018-6-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-209		rzimmerm	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-209	Write section lessons learned	0.5	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-209		rzimmerm	0	0.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-207	Write section achieved result	1.75	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-207		rzimmerm	0	1.75	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-163	Abstract and Mgmt Summary Review	0.75	2018-6-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-163		rzimmerm	0	0.75	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
XGB-207	Write section achieved result	1.75	2018-6-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-207		rzimmerm	0	1.75	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-163	Abstract and Mgmt Summary Review	0.25	2018-6-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-163		rzimmerm	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
XGB-209	Write section lessons learned	1.5	2018-6-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-209		rzimmerm	0	1.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-211	Write section conclusion	0.5	2018-6-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-211		rzimmerm	0	0.5	4	1	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-163	Abstract and Mgmt Summary Review	0.75	2018-6-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-163		rzimmerm	0	0.75	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
XGB-210	Write section future work	0.5	2018-6-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			15m		rzimmerm	0	0.5	4	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-163	Abstract and Mgmt Summary Review	1	2018-6-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-163		rzimmerm	0	1	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
XGB-207	Write section achieved result	0.5	2018-6-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-207		rzimmerm	0	0.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-203	Write section encountered problems	0.25	2018-6-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-203		rzimmerm	0	0.25	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-209	Write section lessons learned	3	2018-6-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-209		rzimmerm	0	3	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-209	Write section lessons learned	2	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-209		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-210	Write section future work	2	2018-6-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-210		rzimmerm	0	2	4	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-211	Write section conclusion	2.5	2018-6-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-211		rzimmerm	0	2.5	4	1	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-203	Write section encountered problems	3	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-203		rzimmerm	0	3	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-208	Collect bullet points for section discussion and conclusion	2	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-208		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-208	Collect bullet points for section discussion and conclusion	2	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-208		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-44	Standup Meetings Sprint 14	0.25	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-44		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-200	Supervision Meeting Sprint 14	0.25	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-200		rzimmerm	0	0.25	2.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-200	Supervision Meeting Sprint 14	0.25	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-200		rzimmerm	0	0.25	2.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-200	Supervision Meeting Sprint 14	1.5	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-200		rzimmerm	0	1.5	2.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-201	Extend install guide in the repository	0.5	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-201		rzimmerm	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-199	Clean Parameter Substitution with breadcrumbs	1	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-199		fhauser	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-201	Extend install guide in the repository	1	2018-6-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-201		rzimmerm	0	1	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-44	Standup Meetings Sprint 14	0.25	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-44		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-200	Supervision Meeting Sprint 14	1	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-200		rzimmerm	0	1	2.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-203	Write section encountered problems	0.5	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-203		rzimmerm	0	0.5	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-199	Clean Parameter Substitution with breadcrumbs	0.5	2018-6-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-199		fhauser	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-191	Document why our dev setup uses bosh (openfire limitations)	0.5	2018-6-3	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-191		rzimmerm	0	0.5	1	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-203	Write section encountered problems	6	2018-6-3	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-203		rzimmerm	0	6	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-201	Extend install guide in the repository	4	2018-6-3	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-201		rzimmerm	0	4	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-201	Extend install guide in the repository	3	2018-6-2	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-201		rzimmerm	0	3	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-16	Infrastructure Updates Sprint 14	0.5	2018-6-1	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-16		fhauser	0	0.5	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-199	Clean Parameter Substitution with breadcrumbs	5.5	2018-6-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-199		fhauser	0	5.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-198	Refactor Error handling	0.5	2018-6-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-198		rzimmerm	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-213	Clean up Layers	0.25	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-213		fhauser	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-213	Clean up Layers	0.5	2018-6-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-213		fhauser	0	0.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-200	Supervision Meeting Sprint 14	1	2018-6-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Setup Support		rzimmerm	0	1	2.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-206	Write section documentation	0.25	2018-6-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-206		rzimmerm	0	0.25	2	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-198	Refactor Error handling	5	2018-6-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-198		rzimmerm	0	5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-205	Write section testing	1	2018-6-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-205		rzimmerm	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-213	Clean up Layers	4	2018-5-31	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-213		fhauser	0	4	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-204	Write section code quality	0.5	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-204		rzimmerm	0	0.5	4	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-202	Write section development setup	0.25	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-202		rzimmerm	0	0.25	2	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-213	Clean up Layers	0.25	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-213		fhauser	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-44	Standup Meetings Sprint 14	0.25	2018-5-31	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-44		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-31	Sprint Planning Sprint 14	0.25	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-31		fhauser	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-31	Sprint Planning Sprint 14	1.5	2018-5-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-31		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-44	Standup Meetings Sprint 14	0.25	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-44		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-194	Introduce barrel imports to simplify imports	0.25	2018-5-31	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Discuss imports		rzimmerm	0	0.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-206	Write section documentation	1	2018-5-30	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-206		rzimmerm	0	1	2	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-194	Introduce barrel imports to simplify imports	2.5	2018-5-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-194		rzimmerm	0	2.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-194	Introduce barrel imports to simplify imports	3	2018-5-30	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-194		rzimmerm	0	3	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-205	Write section testing	1	2018-5-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-205		rzimmerm	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-204	Write section code quality	2	2018-5-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-204		rzimmerm	0	2	4	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-202	Write section development setup	1.5	2018-5-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-202		rzimmerm	0	1.5	2	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-204	Write section code quality	1	2018-5-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			research: complexity tools		rzimmerm	0	1	4	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-31	Sprint Planning Sprint 14	1.5	2018-5-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-31		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
XGB-196	Supervision Meeting Sprint 13	0.75	2018-5-28	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-196		rzimmerm	0	0.75	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-196	Supervision Meeting Sprint 13	0.25	2018-5-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-196		rzimmerm	0	0.25	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-196	Supervision Meeting Sprint 13	1	2018-5-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			docs		rzimmerm	0	1	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-196	Supervision Meeting Sprint 13	0.75	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-196		rzimmerm	0	0.75	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-166	List All Subtopics and Subcollection of a Collection	0.75	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-166		rzimmerm	0	0.75	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-165	List All Parent-Collections of a Topic	0.75	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-165		rzimmerm	0	0.75	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-48	Retrospective 4	1	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-48		fhauser	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-48	Retrospective 4	1	2018-5-28	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-48		fhauser	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-189	Implement breadcrumbs	1.5	2018-5-28	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-189		rzimmerm	0	1.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-43	Standup Meetings Sprint 13	0.5	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-43		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-43	Standup Meetings Sprint 13	0.5	2018-5-28	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-43		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-163	Abstract and Mgmt Summary Review	0.25	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-163		rzimmerm	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
XGB-63	Write Management Summary	0.5	2018-5-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-63		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=], com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 12
XGB-43	Standup Meetings Sprint 13	0.5	2018-5-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-43		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-63	Write Management Summary	0.5	2018-5-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-63		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=], com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 12
XGB-189	Implement breadcrumbs	6	2018-5-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-189		rzimmerm	0	6	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-189	Implement breadcrumbs	1	2018-5-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-189		rzimmerm	0	1	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-189	Implement breadcrumbs	3	2018-5-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-189		rzimmerm	0	3	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-190	Don't show disconnected dialog	0.75	2018-5-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-190		rzimmerm	0	0.75	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-166	List All Subtopics and Subcollection of a Collection	2.5	2018-5-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-166		rzimmerm	0	2.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-165	List All Parent-Collections of a Topic	4	2018-5-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-165		rzimmerm	0	4	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-43	Standup Meetings Sprint 13	0.5	2018-5-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-43		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-63	Write Management Summary	1.5	2018-5-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-63		fhauser	0	1.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=], com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 12
XGB-166	List All Subtopics and Subcollection of a Collection	2	2018-5-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-166		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-190	Don't show disconnected dialog	1.5	2018-5-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-190		rzimmerm	0	1.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-63	Write Management Summary	3	2018-5-24	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-63		fhauser	0	3	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=], com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 12
XGB-193	Split up topic details service into a configuration and affiliation service	0.25	2018-5-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-193		rzimmerm	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-183	Show persisted item tab conditionally	0.5	2018-5-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-183		rzimmerm	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-190	Don't show disconnected dialog	1.5	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-190		rzimmerm	0	1.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-193	Split up topic details service into a configuration and affiliation service	0.25	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-193		rzimmerm	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-183	Show persisted item tab conditionally	0.5	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			fix e2e tests		rzimmerm	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-120	Refactor Links to always use the NavigationService	0.25	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Open	XGB	XMPP-Grid Broker			research		rzimmerm	0	0.25	2.5	2.25		#N/A
XGB-183	Show persisted item tab conditionally	2.5	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-183		rzimmerm	0	2.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-62	Write Abstract	0.5	2018-5-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-62		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-62	Write Abstract	0.5	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-62		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-30	Sprint Planning Sprint 13	1.5	2018-5-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-30		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-30	Sprint Planning Sprint 13	1.5	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-30		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
XGB-62	Write Abstract	0.75	2018-5-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-62		fhauser	0	0.75	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-63	Write Management Summary	0.5	2018-5-21	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-63		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=], com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 12
XGB-62	Write Abstract	2	2018-5-21	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-62		fhauser	0	2	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-169	Inspect Detailed Subscription Configuration	1.5	2018-5-21	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-169		rzimmerm	0	1.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-168	List Consumers	1.5	2018-5-21	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-168		rzimmerm	0	1.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-169	Inspect Detailed Subscription Configuration	2.5	2018-5-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-169		rzimmerm	0	2.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-151	Investigate and document how multiple users can be configured	0.5	2018-5-21	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-151		rzimmerm	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-168	List Consumers	0.5	2018-5-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-168		rzimmerm	0	0.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-171	Unsubscribe Consumer	3	2018-5-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-171		rzimmerm	0	3	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-172	Subscribe Consumer	4	2018-5-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-172		rzimmerm	0	4	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-151	Investigate and document how multiple users can be configured	0.5	2018-5-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-151		rzimmerm	0	0.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-62	Write Abstract	1	2018-5-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-62		fhauser	0	1	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-62	Write Abstract	2.5	2018-5-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-62		fhauser	0	2.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-186	Submit final parts of the final submission document	0.5	2018-5-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-186		rzimmerm	0	0.5	0.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-180	Supervision Meeting Sprint 12	0.25	2018-5-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-180		rzimmerm	0	0.25	1.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-151	Investigate and document how multiple users can be configured	1.5	2018-5-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-151		rzimmerm	0	1.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-168	List Consumers	0.5	2018-5-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-168		rzimmerm	0	0.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-180	Supervision Meeting Sprint 12	0.25	2018-5-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-180		rzimmerm	0	0.25	1.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-180	Supervision Meeting Sprint 12	0.75	2018-5-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-180		rzimmerm	0	0.75	1.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-180	Supervision Meeting Sprint 12	0.75	2018-5-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-180		rzimmerm	0	0.75	1.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-151	Investigate and document how multiple users can be configured	0.75	2018-5-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-151		rzimmerm	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-151	Investigate and document how multiple users can be configured	1.5	2018-5-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-151		rzimmerm	0	1.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-151	Investigate and document how multiple users can be configured	0.75	2018-5-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-151		rzimmerm	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-184	Add "publish new item" on persisted items tab	0.25	2018-5-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-168	List Consumers	2.5	2018-5-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-168		rzimmerm	0	2.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-158	Write e2e test for Topic Details Affiliations View	2.5	2018-5-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-158		rzimmerm	0	2.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-15	Infrastructure Updates Sprint 12	0.75	2018-5-15	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-15		fhauser	0	0.75	1	29.25	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-184	Add "publish new item" on persisted items tab	2	2018-5-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-184		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-15	Infrastructure Updates Sprint 12	0.5	2018-5-15	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-15		fhauser	0	0.5	1	29.25	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-29	Sprint Planning Sprint 12	1.5	2018-5-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-29		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-29	Sprint Planning Sprint 12	1.5	2018-5-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-29		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
XGB-157	Write e2e test for Topic Details Config View	0.75	2018-5-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-157		rzimmerm	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-157	Write e2e test for Topic Details Config View	0.75	2018-5-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Debug and Fix certificate errors		rzimmerm	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-176	Delete a Persisted Item From a Topic	0.5	2018-5-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-176		rzimmerm	0	0.5	3	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-177	Purge All Persisted Items From a Topic	1	2018-5-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	1	4	2.75	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-145	Implement First Language Review	0.5	2018-5-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			review		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-145	Implement First Language Review	6.5	2018-5-14	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-145		fhauser	0	6.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-145	Implement First Language Review	0.75	2018-5-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-145		fhauser	0	0.75	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-158	Write e2e test for Topic Details Affiliations View	3	2018-5-14	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-158		rzimmerm	0	3	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-28	Sprint Planning Sprint 11	1.5	2018-5-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-28		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-175	Paged Persisted Items	4	2018-5-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-175		rzimmerm	0	4	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-177	Purge All Persisted Items From a Topic	0.25	2018-5-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-177		rzimmerm	0	0.25	4	2.75	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-176	Delete a Persisted Item From a Topic	1	2018-5-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-176		rzimmerm	0	1	3	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-157	Write e2e test for Topic Details Config View	4	2018-5-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-157		rzimmerm	0	4	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-175	Paged Persisted Items	0.25	2018-5-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-175		rzimmerm	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-174	Filter Persisted Items	2	2018-5-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Open	XGB	XMPP-Grid Broker			Working on issue XGB-174		rzimmerm	0	2		6		#N/A
XGB-178	Add Persisted Items Tab Component	0.25	2018-5-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.25	1.5	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-150	Investigate Problem with Parenthesis in NodeIDs encoded in the URL	0.5	2018-5-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-150		rzimmerm	0	0.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-178	Add Persisted Items Tab Component	0.5	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-178		rzimmerm	0	0.5	1.5	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-28	Sprint Planning Sprint 11	2	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-28		fhauser	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-175	Paged Persisted Items	3	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			begin with service method implementation		rzimmerm	0	3	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-150	Investigate Problem with Parenthesis in NodeIDs encoded in the URL	1.5	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-150		rzimmerm	0	1.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-134	Implement Paging of Topics on the Topic/Collection Overview pages	1	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Try to make it parallel		rzimmerm	0	1	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-160	Add specialized "Danger Zone" fields for conversion (Topic to collection)	0.25	2018-5-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-160		rzimmerm	0	0.25	1.5	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-150	Investigate Problem with Parenthesis in NodeIDs encoded in the URL	0.5	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-150		rzimmerm	0	0.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
XGB-152	Extend missing pubsub fields in jxt-xmpp	0.5	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-152		rzimmerm	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-145	Implement First Language Review	0.75	2018-5-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-145		fhauser	0	0.75	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-134	Implement Paging of Topics on the Topic/Collection Overview pages	1	2018-5-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-134		rzimmerm	0	1	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-159	Supervision Meeting Sprint 10	0.25	2018-5-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-159		rzimmerm	0	0.25	2.5	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-155	Write e2e test for Overview Tabs	1	2018-5-8	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-155		rzimmerm	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-155	Write e2e test for Overview Tabs	2	2018-5-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Debug failing Travis builds		rzimmerm	0	2	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-155	Write e2e test for Overview Tabs	2	2018-5-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-155		rzimmerm	0	2	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-155	Write e2e test for Overview Tabs	2	2018-5-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-155		rzimmerm	0	2	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-155	Write e2e test for Overview Tabs	2	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-155		rzimmerm	0	2	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-117	Setup e2e Tests Infrastructure	0.5	2018-5-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-117		rzimmerm	0	0.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-134	Implement Paging of Topics on the Topic/Collection Overview pages	1.5	2018-5-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-134		rzimmerm	0	1.5	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-40	Standup Meetings Sprint 10	0.5	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-40		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-40	Standup Meetings Sprint 10	0.25	2018-5-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-40		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-159	Supervision Meeting Sprint 10	0.25	2018-5-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-159		rzimmerm	0	0.25	2.5	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-40	Standup Meetings Sprint 10	0.25	2018-5-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-40		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-159	Supervision Meeting Sprint 10	0.25	2018-5-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-159		rzimmerm	0	0.25	2.5	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-47	Retrospective 3	0.5	2018-5-7	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-47		fhauser	0	0.5	2	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-47	Retrospective 3	0.5	2018-5-7	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-47		fhauser	0	0.5	2	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-134	Implement Paging of Topics on the Topic/Collection Overview pages	5.5	2018-5-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-134		rzimmerm	0	5.5	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-162	Add delete Button in the "Danger Zone" for a Topic	0.25	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-162		rzimmerm	0	0.25	3	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-152	Extend missing pubsub fields in jxt-xmpp	0.25	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-152		rzimmerm	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-149	Fix confusing error shown when the connection to the XMPP server is lost	0.25	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-149		rzimmerm	0	0.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-145	Implement First Language Review	0.25	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-145		fhauser	0	0.25	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
XGB-117	Setup e2e Tests Infrastructure	6	2018-5-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-117		rzimmerm	0	6	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-162	Add delete Button in the "Danger Zone" for a Topic	1	2018-5-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-162		rzimmerm	0	1	3	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-149	Fix confusing error shown when the connection to the XMPP server is lost	0.75	2018-5-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-149		rzimmerm	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-152	Extend missing pubsub fields in jxt-xmpp	1	2018-5-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Write PR & integrate it		rzimmerm	0	1	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-40	Standup Meetings Sprint 10	0.5	2018-5-4	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-40		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-117	Setup e2e Tests Infrastructure	5	2018-5-3	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-117		rzimmerm	0	5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-117	Setup e2e Tests Infrastructure	2.5	2018-5-2	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-117		rzimmerm	0	2.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-161	Implement delete topic service method	0.25	2018-5-2	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-161		rzimmerm	0	0.25	2	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-154	Use pretty confirm dialog in affiliations tab	0.25	2018-5-2	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-154		rzimmerm	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-153	Implement a pretty confirm dialog	0.25	2018-5-2	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-153		rzimmerm	0	0.25	1.5	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-154	Use pretty confirm dialog in affiliations tab	0.25	2018-5-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-154		rzimmerm	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-153	Implement a pretty confirm dialog	1	2018-5-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-153		rzimmerm	0	1	1.5	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-14	Infrastructure Updates Sprint 10	1	2018-5-2	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-14		fhauser	0	1	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-27	Sprint Planning Sprint 10	0.5	2018-5-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-27		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-146	Investigate how paging of Topics/Collections could be implemented	1	2018-5-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-146		rzimmerm	0	1	5	1	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-124	Check XMPP Server Feature Support	1	2018-5-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-124		fhauser	0	1	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-134	Implement Paging of Topics on the Topic/Collection Overview pages	1.25	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-134		rzimmerm	0	1.25	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-162	Add delete Button in the "Danger Zone" for a Topic	0.75	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-162		rzimmerm	0	0.75	3	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-161	Implement delete topic service method	0.75	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-161		rzimmerm	0	0.75	2	1	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-125	Add specialized field component for affiliations	0.75	2018-5-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-125		rzimmerm	0	0.75	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-149	Fix confusing error shown when the connection to the XMPP server is lost	1.25	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-149		rzimmerm	0	1.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-27	Sprint Planning Sprint 10	0.5	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-27		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
XGB-125	Add specialized field component for affiliations	0.5	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-125		rzimmerm	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-124	Check XMPP Server Feature Support	1.5	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-124		fhauser	0	1.5	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-125	Add specialized field component for affiliations	1	2018-5-1	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-125		rzimmerm	0	1	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-124	Check XMPP Server Feature Support	3.5	2018-4-30	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-124		fhauser	0	3.5	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-125	Add specialized field component for affiliations	4.5	2018-4-30	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-125		rzimmerm	0	4.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-124	Check XMPP Server Feature Support	6	2018-4-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-124		fhauser	0	6	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-125	Add specialized field component for affiliations	2.5	2018-4-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-125		rzimmerm	0	2.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-144	Supervisor Meeting Sprint 9a	0.5	2018-4-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Create release and inform Prof. Steffen		fhauser	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-39	Standup Meetings Sprint 9	0.25	2018-4-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-39		fhauser	0	0.25	1	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-140	Discuss Added Value in the Final Submission document	1.25	2018-4-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-140		rzimmerm	0	1.25	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-39	Standup Meetings Sprint 9	0.25	2018-4-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-39		fhauser	0	0.25	1	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-140	Discuss Added Value in the Final Submission document	0.25	2018-4-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-140		rzimmerm	0	0.25	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-146	Investigate how paging of Topics/Collections could be implemented	3	2018-4-29	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-146		rzimmerm	0	3	5	1	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-142	Investigate CSP error in chrome	0.75	2018-4-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-142		rzimmerm	0	0.75	1.5	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-133	Update Client Architecture AD	0.25	2018-4-28	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.25	2	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-147	Isolate configuration in a Component	0.75	2018-4-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.75	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-121	Write configuration/Test drive section in the installation guide	2.5	2018-4-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Test configuration and add deployment		rzimmerm	0	2.5	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-144	Supervisor Meeting Sprint 9a	1	2018-4-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-144		fhauser	0	1	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-144	Supervisor Meeting Sprint 9a	1	2018-4-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-144		fhauser	0	1	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-121	Write configuration/Test drive section in the installation guide	0.75	2018-4-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			review		rzimmerm	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-147	Isolate configuration in a Component	0.5	2018-4-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-121	Write configuration/Test drive section in the installation guide	3.25	2018-4-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-121		rzimmerm	0	3.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-123	Create and Document XMPP-Client Configuration	0.25	2018-4-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Implement Feedback		fhauser	0	0.25	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-138	Error overlay is not displayed when an error during ngOnInit occurs...	0.5	2018-4-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review and Testing		rzimmerm	0	0.5	2	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-147	Isolate configuration in a Component	2	2018-4-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Fix TODOs		rzimmerm	0	2	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-147	Isolate configuration in a Component	1.5	2018-4-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-147		rzimmerm	0	1.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-123	Create and Document XMPP-Client Configuration	0.5	2018-4-25	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			review		fhauser	0	0.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-123	Create and Document XMPP-Client Configuration	7.5	2018-4-24	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-123		fhauser	0	7.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-147	Isolate configuration in a Component	4	2018-4-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-147		rzimmerm	0	4	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-26	Sprint Planning Sprint 9	1	2018-4-24	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-26		fhauser	0	1	3	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-131	Implement create xmpp topic in service	0.75	2018-4-24	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.75	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-138	Error overlay is not displayed when an error during ngOnInit occurs...	0.75	2018-4-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-138		rzimmerm	0	0.75	2	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-133	Update Client Architecture AD	0.5	2018-4-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-133		rzimmerm	0	0.5	2	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-131	Implement create xmpp topic in service	3.25	2018-4-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-131		rzimmerm	0	3.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-26	Sprint Planning Sprint 9	0.5	2018-4-24	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-26		fhauser	0	0.5	3	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-131	Implement create xmpp topic in service	2.5	2018-4-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-131		rzimmerm	0	2.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-139	Interim Presentation	1.5	2018-4-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-139		rzimmerm	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-139	Interim Presentation	1.5	2018-4-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-139		rzimmerm	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9
XGB-123	Create and Document XMPP-Client Configuration	3.75	2018-4-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-123		fhauser	0	3.75	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-38	Standup Meetings Sprint 8	0.5	2018-4-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-38		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-38	Standup Meetings Sprint 8	0.25	2018-4-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-38		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-131	Implement create xmpp topic in service	1.5	2018-4-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Debug		rzimmerm	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-131	Implement create xmpp topic in service	7	2018-4-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-131		rzimmerm	0	7	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-128	Add specialized field component for contained/parent collections	0.5	2018-4-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Rebase and Review		rzimmerm	0	0.5	2.5	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-127	Adapt creation form to create topic OR collection	0.5	2018-4-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Rebase and Review		rzimmerm	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-13	Infrastructure Updates Sprint 8	0.75	2018-4-20	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-13		fhauser	0	0.75	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-126	Add specialized field component for title	0.25	2018-4-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-130	Implement collapsible containers widget	0.5	2018-4-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-130		rzimmerm	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-122	Configure Global Error Handling	0.25	2018-4-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-122		fhauser	0	0.25	2	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-38	Standup Meetings Sprint 8	0.25	2018-4-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-38		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-25	Sprint Planning Sprint 8	0.25	2018-4-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-25		fhauser	0	0.25	3	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-118	Implement TopicOverviewService	2	2018-4-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review and extend promise stucture		rzimmerm	0	2	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-118	Implement TopicOverviewService	1	2018-4-19	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-118		rzimmerm	0	1	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-74	Language Review: Prepare & Submit	0.5	2018-4-18	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-74		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-74	Language Review: Prepare & Submit	0.45	2018-4-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-74		fhauser	0	0.45	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-118	Implement TopicOverviewService	5	2018-4-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Rewrite stuff		rzimmerm	0	5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-118	Implement TopicOverviewService	2.5	2018-4-18	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-118		rzimmerm	0	2.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-128	Add specialized field component for contained/parent collections	1.25	2018-4-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-128		rzimmerm	0	1.25	2.5	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-125	Add specialized field component for affiliations	0.75	2018-4-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-125		rzimmerm	0	0.75	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
XGB-122	Configure Global Error Handling	1	2018-4-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-122		fhauser	0	1	2	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-127	Adapt creation form to create topic OR collection	1.25	2018-4-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-127		rzimmerm	0	1.25	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-118	Implement TopicOverviewService	1.75	2018-4-18	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			review		rzimmerm	0	1.75	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-64	Prepare Interim presentation	0.5	2018-4-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Presentation	Presentation	Presentation		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-118	Implement TopicOverviewService	6	2018-4-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-118		rzimmerm	0	6	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-126	Add specialized field component for title	2	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-126		rzimmerm	0	2	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-126	Add specialized field component for title	1	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-126		rzimmerm	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-130	Implement collapsible containers widget	2	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-130		rzimmerm	0	2	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-64	Prepare Interim presentation	1.5	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Presentation	Presentation	Presentation		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-64		rzimmerm	0	1.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-25	Sprint Planning Sprint 8	1	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-25		fhauser	0	1	3	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-25	Sprint Planning Sprint 8	1	2018-4-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-25		fhauser	0	1	3	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
XGB-114	Advisory Meeting Sprint 7	0.25	2018-4-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-114		rzimmerm	0	0.25	1.5	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-116	Implement dynamic handling of XMPP data forms	0.5	2018-4-17	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.5	12	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-74	Language Review: Prepare & Submit	1	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-74		fhauser	0	1	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-97	Conduct an architectural analysis with an industry expert	1	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-97		rzimmerm	0	1	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-114	Advisory Meeting Sprint 7	0.5	2018-4-17	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Meeting Minutes		rzimmerm	0	0.5	1.5	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-118	Implement TopicOverviewService	5	2018-4-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-118		rzimmerm	0	5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-116	Implement dynamic handling of XMPP data forms	3	2018-4-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-116		rzimmerm	0	3	12	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-37	Standup Meetings Sprint 7	0.5	2018-4-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-37		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-37	Standup Meetings Sprint 7	0.5	2018-4-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-37		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-97	Conduct an architectural analysis with an industry expert	0.25	2018-4-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-97		rzimmerm	0	0.25	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-97	Conduct an architectural analysis with an industry expert	0.75	2018-4-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-97		rzimmerm	0	0.75	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-97	Conduct an architectural analysis with an industry expert	0.5	2018-4-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-97		rzimmerm	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-114	Advisory Meeting Sprint 7	0.25	2018-4-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-114		rzimmerm	0	0.25	1.5	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-118	Implement TopicOverviewService	7	2018-4-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-118		rzimmerm	0	7	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-116	Implement dynamic handling of XMPP data forms	2.5	2018-4-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-116		rzimmerm	0	2.5	12	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-99	Define and Document Content Security Policy	0.25	2018-4-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-99		fhauser	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=], com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 6
XGB-119	Finish NGINX Setup	1	2018-4-15	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-119		fhauser	0	1	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-99	Define and Document Content Security Policy	0.5	2018-4-15	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-99		fhauser	0	0.5	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=], com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 6
XGB-116	Implement dynamic handling of XMPP data forms	4.5	2018-4-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-116		rzimmerm	0	4.5	12	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-119	Finish NGINX Setup	0.25	2018-4-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			review		fhauser	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-119	Finish NGINX Setup	1	2018-4-10	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-119		fhauser	0	1	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-119	Finish NGINX Setup	2	2018-4-11	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-119		fhauser	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-119	Finish NGINX Setup	2	2018-4-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-119		fhauser	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-116	Implement dynamic handling of XMPP data forms	1	2018-4-11	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-116		rzimmerm	0	1	12	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-116	Implement dynamic handling of XMPP data forms	4.5	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-116		rzimmerm	0	4.5	12	0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-115	Analyze XMPP Data Form Fields and Provide UI-Mockups for each	1	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-115		rzimmerm	0	1	3.5	2.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-46	Retrospective 2	0.25	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-46		fhauser	0	0.25	2	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-46	Retrospective 2	0.25	2018-4-10	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-46		fhauser	0	0.25	2	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-24	Sprint Planning Sprint 7	0.5	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-24		fhauser	0	0.5	3	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-24	Sprint Planning Sprint 7	0.25	2018-4-10	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-24		fhauser	0	0.25	3	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-113	Advisory Meeting Sprint 6	0.75	2018-4-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-113		rzimmerm	0	0.75		0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-107	Final Framework Decision: XMPP-Framework	0.25	2018-4-10	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.25	12	9.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-110	Write Tests for existing Components	0.25	2018-4-10	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review Feedback		rzimmerm	0	0.25	8	4.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-110	Write Tests for existing Components	0.5	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-110		rzimmerm	0	0.5	8	4.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-24	Sprint Planning Sprint 7	0.5	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Plann next Sprint		fhauser	0	0.5	3	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-64	Prepare Interim presentation	0.5	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Presentation	Presentation	Presentation		Task	Done	XGB	XMPP-Grid Broker			Write Mail		rzimmerm	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-107	Final Framework Decision: XMPP-Framework	1	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Try out basic implementation		fhauser	0	1	12	9.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-107	Final Framework Decision: XMPP-Framework	1	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-107		fhauser	0	1	12	9.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-113	Advisory Meeting Sprint 6	0.5	2018-4-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Meeting Minutes		rzimmerm	0	0.5		0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-113	Advisory Meeting Sprint 6	0.5	2018-4-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Meeting		rzimmerm	0	0.5		0	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-36	Standup Meetings Sprint 6	0.5	2018-4-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-36		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-24	Sprint Planning Sprint 7	0.5	2018-4-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-24		fhauser	0	0.5	3	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
XGB-86	Investigate how XMPP over WebSockets could be proxied	0.25	2018-4-10	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-86		rzimmerm	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 4
XGB-111	Clean up tab view implementation	0.5	2018-4-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-111		rzimmerm	0	0.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-109	Extract Topic List Component	1	2018-4-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-109		rzimmerm	0	1	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-108	Implement Mock Service to fetch topics/collections in overview	2	2018-4-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-108		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-36	Standup Meetings Sprint 6	0.5	2018-4-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-36		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-86	Investigate how XMPP over WebSockets could be proxied	0.75	2018-4-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-86		rzimmerm	0	0.75	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 4
XGB-110	Write Tests for existing Components	1.5	2018-4-3	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-110		rzimmerm	0	1.5	8	4.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-111	Clean up tab view implementation	1.5	2018-4-3	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-111		rzimmerm	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-109	Extract Topic List Component	3	2018-4-3	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-109		rzimmerm	0	3	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-108	Implement Mock Service to fetch topics/collections in overview	2	2018-4-3	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-108		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-23	Sprint Planning Sprint 6	0.5	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-23		fhauser	0	0.5	0.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-86	Investigate how XMPP over WebSockets could be proxied	0.5	2018-4-3	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-86		rzimmerm	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 4
XGB-106	Set up NGINX to proxy openfire BOSH	1.5	2018-3-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-106		fhauser	0	1.5	4	2.5	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-86	Investigate how XMPP over WebSockets could be proxied	0.5	2018-3-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-86		rzimmerm	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 4
XGB-105	Add Co-Examiner to first submission document page & move task description	0.25	2018-3-29	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-105		fhauser	0	0.25	0.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-110	Write Tests for existing Components	1	2018-3-28	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-110		rzimmerm	0	1	8	4.75	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-12	Infrastructure Updates Sprint 6	1.75	2018-3-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-12		fhauser	0	1.75	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-23	Sprint Planning Sprint 6	0.5	2018-3-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-23		fhauser	0	0.5	0.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-111	Clean up tab view implementation	0.25	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-111		rzimmerm	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-112	Understand Angular Observables	2.5	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-112		rzimmerm	0	2.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-111	Clean up tab view implementation	1	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-111		rzimmerm	0	1	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
XGB-102	Draw angular component/module map	0.5	2018-3-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-100	Supervisor Meeting Sprint 5	0.25	2018-3-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.25	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-101	Client TLS Certificate Authentication	3	2018-3-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-101		fhauser	0	3	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-101	Client TLS Certificate Authentication	0.25	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			review		fhauser	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-98	Analyse XMPP Server XSRF attacks	4.5	2018-3-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-98		fhauser	0	4.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-88	Framework Decision: XMPP Framework	8	2018-3-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-88		fhauser	0	8	8	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 4
XGB-101	Client TLS Certificate Authentication	0.25	2018-3-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-101		fhauser	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-35	Standup Meetings Sprint 5	0.25	2018-3-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-35		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-35	Standup Meetings Sprint 5	0.5	2018-3-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-35		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-35	Standup Meetings Sprint 5	0.5	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-35		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-103	Learn about Testing/Mocking (e2e, unit)	1	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-103		rzimmerm	0	1	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-94	Setup openfire with CA / Client Certificates for development	0.25	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-94		fhauser	0	0.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-100	Supervisor Meeting Sprint 5	0.5	2018-3-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-100		fhauser	0	0.5	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-35	Standup Meetings Sprint 5	0.25	2018-3-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-35		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-103	Learn about Testing/Mocking (e2e, unit)	5	2018-3-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-103		rzimmerm	0	5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-94	Setup openfire with CA / Client Certificates for development	0.25	2018-3-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-94		fhauser	0	0.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-101	Client TLS Certificate Authentication	1	2018-3-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-101		fhauser	0	1	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-101	Client TLS Certificate Authentication	3	2018-3-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-101		fhauser	0	3	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-94	Setup openfire with CA / Client Certificates for development	2	2018-3-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-94		fhauser	0	2	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-100	Supervisor Meeting Sprint 5	1	2018-3-23	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-100		fhauser	0	1	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-102	Draw angular component/module map	1	2018-3-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-102		rzimmerm	0	1	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-100	Supervisor Meeting Sprint 5	1	2018-3-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-100		fhauser	0	1	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-104	Implement "Overview"-Views	4.75	2018-3-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-104		rzimmerm	0	4.75	8	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-104	Implement "Overview"-Views	1	2018-3-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-104		rzimmerm	0	1	8	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-104	Implement "Overview"-Views	2	2018-3-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-104		rzimmerm	0	2	8	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-102	Draw angular component/module map	2	2018-3-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-102		rzimmerm	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-61	Attach Signed Task Description to Submission Document	0.25	2018-3-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-61		fhauser	0	0.25	0.25	0	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-22	Sprint Planning Sprint 5	1	2018-3-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-22		fhauser	0	1	3	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-22	Sprint Planning Sprint 5	1	2018-3-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-22		fhauser	0	1	3	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-93	Write Section "Risk Analysis"	0.25	2018-3-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-93		rzimmerm	0	0.25	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-93	Write Section "Risk Analysis"	2.5	2018-3-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-93		rzimmerm	0	2.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-90	Write Section "Domain Analysis"	0.25	2018-3-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-22	Sprint Planning Sprint 5	0.25	2018-3-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-22		fhauser	0	0.25	3	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
XGB-34	Standup Meetings Sprint 4	0.5	2018-3-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-34		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-90	Write Section "Domain Analysis"	1.5	2018-3-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-90		fhauser	0	1.5	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-89	Write Section "Requirements / Analysis"	0.5	2018-3-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-91		fhauser	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-87	Bootstrap Angular	0.25	2018-3-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-87		fhauser	0	0.25	4	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-96	Learning Angular	2.25	2018-3-19	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-96		fhauser	0	2.25	15	8	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-34	Standup Meetings Sprint 4	0.5	2018-3-19	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-34		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-92	Write Section "Architecture"	1.25	2018-3-19	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-92		fhauser	0	1.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-96	Learning Angular	2	2018-3-18	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-96		fhauser	0	2	15	8	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-95	Security Considerations in Concept Section	0.5	2018-3-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-11	Infrastructure Updates Sprint 4	0.75	2018-3-16	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-11		fhauser	0	0.75	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-89	Write Section "Requirements / Analysis"	1.75	2018-3-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-89		fhauser	0	1.75	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-87	Bootstrap Angular	0.75	2018-3-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-87		fhauser	0	0.75	4	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-34	Standup Meetings Sprint 4	0.25	2018-3-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-34		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-92	Write Section "Architecture"	4	2018-3-14	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-92		fhauser	0	4	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-92	Write Section "Architecture"	2	2018-3-16	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-92		fhauser	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-96	Learning Angular	0.75	2018-3-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-96		fhauser	0	0.75	15	8	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-34	Standup Meetings Sprint 4	0.25	2018-3-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-34		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-95	Security Considerations in Concept Section	2.5	2018-3-16	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-95		fhauser	0	2.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-91	Write Section "Wireframes"	0.5	2018-3-14	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-91		rzimmerm	0	0.5	2	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-92	Write Section "Architecture"	1	2018-3-13	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-92		fhauser	0	1	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-96	Learning Angular	1.25	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-96		fhauser	0	1.25	15	8	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-87	Bootstrap Angular	2.75	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-87		fhauser	0	2.75	4	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-96	Learning Angular	0.75	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-96		fhauser	0	0.75	15	8	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-91	Write Section "Wireframes"	0.5	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-91		rzimmerm	0	0.5	2	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-89	Write Section "Requirements / Analysis"	2	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-89		fhauser	0	2	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-21	Sprint Planning Sprint 4	0.25	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-21		fhauser	0	0.25	1	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-21	Sprint Planning Sprint 4	0.5	2018-3-13	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-21		fhauser	0	0.5	1	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
XGB-45	Retrospective 1	0.25	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-45		fhauser	0	0.25	2	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-45	Retrospective 1	0.25	2018-3-13	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-45		fhauser	0	0.25	2	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-75	Create Architecture Overview	1	2018-3-11	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-75		fhauser	0	1	5	4	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-83	Architectural Decision: Frontend Framework	0.25	2018-3-13	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-13	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	1	2018-3-13	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	1	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-83	Architectural Decision: Frontend Framework	2	2018-3-11	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-83		rzimmerm	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-80	Architectural Decision: REST vs. BOSH XMPP vs. WebSockets	0.75	2018-3-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-82		rzimmerm	0	0.75	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-83	Architectural Decision: Frontend Framework	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-83		rzimmerm	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-85	Compare Jabber Servers and Client Libraries	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-85		fhauser	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-80	Architectural Decision: REST vs. BOSH XMPP vs. WebSockets	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker					rzimmerm	0	0.25	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Discuss state management		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-81	Architectural Decision: State Management (TCP Connection)	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-81		rzimmerm	0	0.25	4	1.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-60	Plan Final Submission Document Outline	0.25	2018-3-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-60		fhauser	0	0.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-76	Supervision Meeting Sprint 3	0.25	2018-3-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-76		rzimmerm	0	0.25	4	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-76	Supervision Meeting Sprint 3	0.5	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-76		rzimmerm	0	0.5	4	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-76	Supervision Meeting Sprint 3	1	2018-3-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-76		rzimmerm	0	1	4	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-76	Supervision Meeting Sprint 3	0.75	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-76		rzimmerm	0	0.75	4	1.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-60	Plan Final Submission Document Outline	0.25	2018-3-12	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-60		fhauser	0	0.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-84	Architectural Decision: SASL	0.25	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-84		rzimmerm	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-60	Plan Final Submission Document Outline	0.75	2018-3-12	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-60		fhauser	0	0.75	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-85	Compare Jabber Servers and Client Libraries	2.5	2018-3-11	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-85		fhauser	0	2.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-84	Architectural Decision: SASL	1.5	2018-3-11	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-84		rzimmerm	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-77	Finalise User Stories and Wireframes	0.25	2018-3-11	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-77		rzimmerm	0	0.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-77	Finalise User Stories and Wireframes	0.25	2018-3-11	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-77		rzimmerm	0	0.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-84	Architectural Decision: SASL	1.5	2018-3-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Research		rzimmerm	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-77	Finalise User Stories and Wireframes	2	2018-3-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-77		rzimmerm	0	2	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-60	Plan Final Submission Document Outline	1.25	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-60		fhauser	0	1.25	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-78	Architectural Decision: Web Application	0.5	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-78		rzimmerm	0	0.5	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-78	Architectural Decision: Web Application	0.5	2018-3-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-78		rzimmerm	0	0.5	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-78	Architectural Decision: Web Application	0.5	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-78		rzimmerm	0	0.5	2	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-80	Architectural Decision: REST vs. BOSH XMPP vs. WebSockets	1	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-80		rzimmerm	0	1	3	0.25	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-33	Standup Meetings Sprint 3	0.25	2018-3-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-33		fhauser	0	0.25	1	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-79	Architectural Decision: Roles	0.25	2018-3-9	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Discussion and Review		rzimmerm	0	0.25	4	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-33	Standup Meetings Sprint 3	0.25	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-33		fhauser	0	0.25	1	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-77	Finalise User Stories and Wireframes	2.25	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-77		rzimmerm	0	2.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-79	Architectural Decision: Roles	0.25	2018-3-9	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-79		rzimmerm	0	0.25	4	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-85	Compare Jabber Servers and Client Libraries	2	2018-3-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-85		fhauser	0	2	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-83	Architectural Decision: Frontend Framework	1.25	2018-3-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-83		rzimmerm	0	1.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-79	Architectural Decision: Roles	0.75	2018-3-8	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-79		rzimmerm	0	0.75	4	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-77	Finalise User Stories and Wireframes	1.5	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-77		rzimmerm	0	1.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-77	Finalise User Stories and Wireframes	0.5	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-77		rzimmerm	0	0.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-83	Architectural Decision: Frontend Framework	1.5	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-83		rzimmerm	0	1.5	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-79	Architectural Decision: Roles	1	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-79		rzimmerm	0	1	4	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-20	Sprint Planning Sprint 3	0.5	2018-3-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-20		fhauser	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-20	Sprint Planning Sprint 3	0.5	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Sprint planning		fhauser	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-72	Collect Jabber Servers and Jabber Client Libraries	0.5	2018-3-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-72		rzimmerm	0	0.5	4.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-79	Architectural Decision: Roles	1	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-79		rzimmerm	0	1	4	0.75	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-73	Supervision Meeting Sprint 2	0.25	2018-3-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-73	Supervision Meeting Sprint 2	1	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-73		fhauser	0	1	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-83	Architectural Decision: Frontend Framework	0.25	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-83		rzimmerm	0	0.25	4	0	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-69	Architectural Decision: Plugin, Component or Bot	0.25	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-69		fhauser	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-67	Extend Background / Publish-Subscribe chapter	0.25	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review / Improve language		fhauser	0	0.25	6	3.75	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	0.25	2018-3-6	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	0.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-69	Architectural Decision: Plugin, Component or Bot	0.75	2018-3-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-69		fhauser	0	0.75	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-72	Collect Jabber Servers and Jabber Client Libraries	2	2018-3-6	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-72		rzimmerm	0	2	4.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-20	Sprint Planning Sprint 3	0.75	2018-3-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-20		fhauser	0	0.75	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-69	Architectural Decision: Plugin, Component or Bot	0.75	2018-3-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-69		fhauser	0	0.75	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-20	Sprint Planning Sprint 3	0.75	2018-3-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-20		fhauser	0	0.75	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
XGB-73	Supervision Meeting Sprint 2	2	2018-3-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Meeting		fhauser	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-32	Standup Meetings Sprint 2	0.25	2018-3-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-32		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-32	Standup Meetings Sprint 2	0.5	2018-3-5	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-32		fhauser	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-73	Supervision Meeting Sprint 2	2	2018-3-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-73		fhauser	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-32	Standup Meetings Sprint 2	0.25	2018-3-5	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-32		fhauser	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-72	Collect Jabber Servers and Jabber Client Libraries	2	2018-3-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-72		rzimmerm	0	2	4.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-69	Architectural Decision: Plugin, Component or Bot	1.5	2018-3-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-69		fhauser	0	1.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	0.75	2018-3-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	0.75	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-71	Create Wireframes	0.5	2018-3-4	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-67	Extend Background / Publish-Subscribe chapter	1	2018-3-2	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-67		fhauser	0	1	6	3.75	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	0.5	2018-3-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			finish up & rebase		fhauser	0	0.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-71	Create Wireframes	1.5	2018-3-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-71		fhauser	0	1.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	3.25	2018-3-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	3.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-71	Create Wireframes	1.5	2018-3-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Try to build wireframes with vue - without success :(		fhauser	0	1.5	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-72	Collect Jabber Servers and Jabber Client Libraries	0.5	2018-2-28	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-72		rzimmerm	0	0.5	4.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-65	Write Background introduction chapter	0.25	2018-3-2	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-65		fhauser	0	0.25	5	2.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-67	Extend Background / Publish-Subscribe chapter	1	2018-3-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-67		fhauser	0	1	6	3.75	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	0.25	2018-3-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	0.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-65	Write Background introduction chapter	0.25	2018-3-1	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-65		fhauser	0	0.25	5	2.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-65	Write Background introduction chapter	0.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-65		fhauser	0	0.25	5	2.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-68	Prepare Architectural Decision templates	0.5	2018-2-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	0.5	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-59	Clearify Document Language Review	0.5	2018-2-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-59		fhauser	0	0.5	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	1.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	1.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-68	Prepare Architectural Decision templates	0.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-68		fhauser	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-65	Write Background introduction chapter	1.75	2018-2-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-65		fhauser	0	1.75	5	2.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-68	Prepare Architectural Decision templates	0.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-68		fhauser	0	0.25	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	2.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	2.25	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-66	Define and correct terminology in Background Chapter	0.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-66		fhauser	0	0.25	5	2	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-66	Define and correct terminology in Background Chapter	1.25	2018-2-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review / Read term definitions in standards		fhauser	0	1.25	5	2	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-71	Create Wireframes	0.25	2018-2-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Application	Application	Application		Task	Done	XGB	XMPP-Grid Broker			Organise Balsamiq account		fhauser	0	0.25	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-70	Create Quality User Stories	0.5	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-70		fhauser	0	0.5	5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-66	Define and correct terminology in Background Chapter	1.5	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-66		fhauser	0	1.5	5	2	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-10	Infrastructure Updates Sprint 2	0.75	2018-2-27	fhauser	Fabian Hauser		RED-SA	Redbackup SA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-10		fhauser	0	0.75	0.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-18	Analyse and test existing python proof-of-concept	0.5	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-18		fhauser	0	0.5	7	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-19	Sprint Planning Sprint 2	1.25	2018-2-27	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-19		fhauser	0	1.25	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-19	Sprint Planning Sprint 2	1.25	2018-2-27	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-19		fhauser	0	1.25	3	0.5	[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
XGB-18	Analyse and test existing python proof-of-concept	1	2018-2-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		fhauser	0	1	7	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-5	Weekly Meeting with SFF	0.5	2018-2-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Review / Typos / Resulting corrections		rzimmerm	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-5	Weekly Meeting with SFF	1.25	2018-2-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Meeting		rzimmerm	0	1.25	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	1.5	2018-2-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	1.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-18	Analyse and test existing python proof-of-concept	0.25	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker					fhauser	0	0.25	7	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-18	Analyse and test existing python proof-of-concept	0.25	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-18		fhauser	0	0.25	7	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-5	Weekly Meeting with SFF	0.5	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			preparation		rzimmerm	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-17	Prepare management issues and compile checklists	0.25	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-17		fhauser	0	0.25	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	0.5	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			review		rzimmerm	0	0.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-5	Weekly Meeting with SFF	0.5	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-5		rzimmerm	0	0.5	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	0.5	2018-2-25	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Review		rzimmerm	0	0.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-5	Weekly Meeting with SFF	1	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Meeting		rzimmerm	0	1	2.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-7	Standup Meetings Sprint 1	0.25	2018-2-26	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-7		rzimmerm	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-7	Standup Meetings Sprint 1	0.25	2018-2-26	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-7		rzimmerm	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-18	Analyse and test existing python proof-of-concept	1.25	2018-2-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-18		fhauser	0	1.25	7	1.75	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	1	2018-2-23	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	1	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	4.25	2018-2-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	4.25	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-17	Prepare management issues and compile checklists	1	2018-2-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-17		fhauser	0	1	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-7	Standup Meetings Sprint 1	0.25	2018-2-22	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-7		rzimmerm	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-7	Standup Meetings Sprint 1	0.25	2018-2-22	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-7		rzimmerm	0	0.25	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-17	Prepare management issues and compile checklists	0.75	2018-2-21	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-17		fhauser	0	0.75	1.5	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	0.5	2018-2-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	0.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	0.5	2018-2-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	0.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-3	Deploy latest documents on the website using CI	0.5	2018-2-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-3		rzimmerm	0	0.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	1.5	2018-2-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	1.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	0.25	2018-2-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	0.25	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-3	Deploy latest documents on the website using CI	0.25	2018-2-21	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			troubleshooting		rzimmerm	0	0.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	2.5	2018-2-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-8		rzimmerm	0	2.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-3	Deploy latest documents on the website using CI	0.5	2018-2-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-3		rzimmerm	0	0.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-8	Write section "Initial Position" based on the IETF and XEP standards	2.5	2018-2-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Final Submission Document	Final Submission Document	Final Submission Document		Task	Done	XGB	XMPP-Grid Broker			Digest standards		rzimmerm	0	2.5	10	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-3	Deploy latest documents on the website using CI	1.25	2018-2-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-3		rzimmerm	0	1.25	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-3	Deploy latest documents on the website using CI	2	2018-2-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker					rzimmerm	0	2	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-3	Deploy latest documents on the website using CI	0.5	2018-2-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-3		rzimmerm	0	0.5	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-4	Sprint Planning Sprint 1	0.5	2018-2-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-4		rzimmerm	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-9	Installation Backup Server	3	2018-2-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-9		fhauser	0	3	3	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-4	Sprint Planning Sprint 1	0.5	2018-2-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-4		rzimmerm	0	0.5	1	0	[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
XGB-6	Kickoff Meeting rzimmerm & fhauser	2	2018-2-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-6		rzimmerm	0	2	4	1	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
XGB-2	Create project plan	1	2018-2-20	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-2		rzimmerm	0	1	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
XGB-2	Create project plan	2.5	2018-2-20	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-2		rzimmerm	0	2.5	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
XGB-2	Create project plan	3	2018-2-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Project Plan	Project Plan	Project Plan		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-2		rzimmerm	0	3	6	0	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
XGB-1	Kickoff Meeting with SFF	1	2018-2-19	fhauser	Fabian Hauser		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-1		rzimmerm	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
XGB-6	Kickoff Meeting rzimmerm & fhauser	1	2018-2-19	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-6		rzimmerm	0	1	4	1	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
XGB-1	Kickoff Meeting with SFF	1	2018-2-19	rzimmerm	Raphael Zimmermann		XGBBA	XGB BA	fhauser			Management	Management	Management		Task	Done	XGB	XMPP-Grid Broker			Working on issue XGB-1		rzimmerm	0	1	2	0	[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0

## time_per_sprint_per_person
Full name	Esprint	Sum - Hours
Fabian Hauser	Sprint 0	7
	Sprint 1	14.25
	Sprint 2	19.5
	Sprint 3	18.5
	Sprint 4	28.5
	Sprint 5	18
	Sprint 6	9
	Sprint 7	32.2
	Sprint 8	35.25
	Sprint 9	9.25
	Sprint 10	43
	Sprint 11	4
	Sprint 12	21.25
	Sprint 13	24.25
	Sprint 14	41.75
	Sprint 15	14.25
Raphael Zimmermann	Sprint 0	4.5
	Sprint 1	20.25
	Sprint 2	20.25
	Sprint 3	20.75
	Sprint 4	16.25
	Sprint 5	20.5
	Sprint 6	16.5
	Sprint 7	34.25
	Sprint 8	34.75
	Sprint 9	15.25
	Sprint 10	24.25
	Sprint 11	12.75
	Sprint 12	22.5
	Sprint 13	24
	Sprint 14	35
	Sprint 15	16.5
	#N/A	2.25
Total Result		680.45

## sprint_alias
Full Key	Sprint Name
[com.atlassian.greenhopper.service.sprint.Sprint@2270a3cc[id=39,rapidViewId=7,state=CLOSED,name=Sprint 0,startDate=2018-02-19T11:31:02.790+01:00,endDate=2018-02-20T14:00:00.000+01:00,completeDate=2018-02-20T10:36:58.133+01:00,sequence=39,goal=Kickoff]]	Sprint 0
[com.atlassian.greenhopper.service.sprint.Sprint@128d933a[id=40,rapidViewId=7,state=CLOSED,name=Sprint 1,startDate=2018-02-20T10:51:12.623+01:00,endDate=2018-02-27T20:40:00.000+01:00,completeDate=2018-02-27T08:33:41.208+01:00,sequence=40,goal=<null>]]	Sprint 1
[com.atlassian.greenhopper.service.sprint.Sprint@3d772648[id=41,rapidViewId=7,state=CLOSED,name=Sprint 2,startDate=2018-02-27T09:32:08.779+01:00,endDate=2018-03-06T12:00:00.000+01:00,completeDate=2018-03-06T10:20:00.506+01:00,sequence=41,goal=]]	Sprint 2
[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=], com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 10
[com.atlassian.greenhopper.service.sprint.Sprint@7c93c065[id=49,rapidViewId=7,state=CLOSED,name=Sprint 10,startDate=2018-05-01T23:52:23.282+02:00,endDate=2018-05-08T10:00:00.000+02:00,completeDate=2018-05-08T14:00:32.223+02:00,sequence=49,goal=]]	Sprint 10
[com.atlassian.greenhopper.service.sprint.Sprint@77492279[id=50,rapidViewId=7,state=CLOSED,name=Sprint 11,startDate=2018-05-08T14:00:51.372+02:00,endDate=2018-05-15T02:00:00.000+02:00,completeDate=2018-05-15T14:05:44.645+02:00,sequence=50,goal=]]	Sprint 11
[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=], com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 12
[com.atlassian.greenhopper.service.sprint.Sprint@39cb9df2[id=51,rapidViewId=7,state=CLOSED,name=Sprint 12,startDate=2018-05-15T14:09:53.216+02:00,endDate=2018-05-22T10:00:00.000+02:00,completeDate=2018-05-22T12:34:00.235+02:00,sequence=51,goal=]]	Sprint 12
[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=], com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 13
[com.atlassian.greenhopper.service.sprint.Sprint@1d71abcb[id=52,rapidViewId=7,state=CLOSED,name=Sprint 13,startDate=2018-05-22T12:34:49.311+02:00,endDate=2018-05-29T10:00:00.000+02:00,completeDate=2018-05-31T10:40:39.074+02:00,sequence=52,goal=]]	Sprint 13
[com.atlassian.greenhopper.service.sprint.Sprint@627a2372[id=70,rapidViewId=7,state=CLOSED,name=Sprint 14,startDate=2018-05-31T10:41:19.937+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=2018-06-06T11:09:44.227+02:00,sequence=53,goal=]]	Sprint 14
[com.atlassian.greenhopper.service.sprint.Sprint@5b38caa0[id=68,rapidViewId=7,state=ACTIVE,name=Sprint 15,startDate=2018-06-06T11:25:13.055+02:00,endDate=2018-06-12T10:00:00.000+02:00,completeDate=<null>,sequence=68,goal=]]	Sprint 15
[com.atlassian.greenhopper.service.sprint.Sprint@54cb344d[id=42,rapidViewId=7,state=CLOSED,name=Sprint 3,startDate=2018-03-06T10:21:16.380+01:00,endDate=2018-03-13T14:00:00.000+01:00,completeDate=2018-03-13T10:42:42.824+01:00,sequence=42,goal=]]	Sprint 3
[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 4
[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=], com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 4
[com.atlassian.greenhopper.service.sprint.Sprint@62744682[id=43,rapidViewId=7,state=CLOSED,name=Sprint 4,startDate=2018-03-13T10:44:37.350+01:00,endDate=2018-03-20T14:22:00.000+01:00,completeDate=2018-03-20T14:11:01.403+01:00,sequence=43,goal=]]	Sprint 4
[com.atlassian.greenhopper.service.sprint.Sprint@44507ff0[id=44,rapidViewId=7,state=CLOSED,name=Sprint 5,startDate=2018-03-20T14:49:54.386+01:00,endDate=2018-03-27T15:00:00.000+02:00,completeDate=2018-03-27T16:34:40.473+02:00,sequence=44,goal=]]	Sprint 5
[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=], com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 6
[com.atlassian.greenhopper.service.sprint.Sprint@368bd491[id=45,rapidViewId=7,state=CLOSED,name=Sprint 6,startDate=2018-03-27T16:47:13.206+02:00,endDate=2018-04-03T16:58:00.000+02:00,completeDate=2018-04-10T11:02:40.147+02:00,sequence=45,goal=]]	Sprint 6
[com.atlassian.greenhopper.service.sprint.Sprint@6c9aa27c[id=46,rapidViewId=7,state=CLOSED,name=Sprint 7,startDate=2018-04-10T11:05:38.898+02:00,endDate=2018-04-17T14:30:00.000+02:00,completeDate=2018-04-19T13:16:21.529+02:00,sequence=46,goal=]]	Sprint 7
[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=], com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 8
[com.atlassian.greenhopper.service.sprint.Sprint@1fc7fafc[id=47,rapidViewId=7,state=CLOSED,name=Sprint 8,startDate=2018-04-19T13:18:51.279+02:00,endDate=2018-04-26T16:43:00.000+02:00,completeDate=2018-04-24T15:21:07.763+02:00,sequence=47,goal=]]	Sprint 8
[com.atlassian.greenhopper.service.sprint.Sprint@40615720[id=48,rapidViewId=7,state=CLOSED,name=Sprint 9,startDate=2018-04-24T15:21:10.524+02:00,endDate=2018-05-01T23:00:00.000+02:00,completeDate=2018-05-01T23:52:20.269+02:00,sequence=48,goal=]]	Sprint 9